## Product Backlog
Product Backlog Items (PBI's)
| Project Name: CustomOffice Newsletter Project | Newsletter Project
| User Story or Feature (Functionality) |  |  | Estimate in Points | Acceptance Criteria | Rationale for Priortization | Notes | Sprint #
| As a | I want to | So that I can
| As a member of the executive team, | I want to have the newsletter in Microsoft Word format, | So that I can distribute it internally for a series of input and feedback opportunities prior to publication. | 10 | The newsletter is in Microsoft Word format | This task has a high priority because it will provide an opportunity for critical feedback from stakeholders to improve the newsletter prior to publication. | High priority | 1
| As a member of the executive team, | I want to be able to see the development history and progress of the document, | So that I can see the work in progress, track how the newsletter evolved, and view who worked on it | 10 | The document shows who worked on it and the changes made to it during development. | This task has a high priority because it will commnunicate the progress, the direction, and the accomplishments made on the document. It will also offer insight into the individuals who were responsible for each section of the newsletter. | High priority | 1
| As the CEO, | I want to have a "Note from the CEO" section with a picture of myself in the newsletter that welcomes readers to the inaugural version of the newsletter | So that I can introduce myself and provide a face of the company to readers. | 20 | This document has an introduction with a section on a "Note from the CEO," including a beautiful picture of the CEO and a 125-200 word description that welcomes readers and mentions his/her excitement to provide the newsletter to customers. | This task has a high priority because the CEO of the company has asked for it, and he has significant authority and power over the project. | High priority | 1
| As a reader, | I want the newsletter to have a feature story on the proper height for a PC monitor, | So that I can understand the ergonomic benefits and how to achieve the optimal height in my home. | 50 | The newsletter contains a 200-500 word section on the feature story, which describes the right height for a PC monitor, an address on the controvery over the proper height, options to achieve the proper height, and a sketch showing the process. | This task has a high priority because it is the main feature and article of the newsletter. | High priority | 1
| As a member of the executive team, | I want a product review on the Flexi-Light that includes a teaser phrase and a link. | So that I can appeal to the readers interests and promote one of our products. | 30 | This section must not include a photo, however, it must include a 100 word product review on the features of the Flexi-Light with a catch-phrase: "want to see what it looks like?" and a link to the product page. | This task has a high priority because the executive team has determined it to be "highly desirable." This task has the potential to not only appeal to the readers interests but promote CustomOffice's products as well. | High priority. | 1
| As a member of the executive team, | I want the publication to have a special offer to the first 25 people who email in a question or suggestion for the upcoming issue of the newsletter, and send them a free CO Coffee mug | So that I can incentivize readers to submit ideas for content for upcoming issues and capture readership. | 25 | The special offer should be less than 100 words but include some sort of graphic next to the text to capture interest. The text must include instructions for the reader to provide a shipping address and their name. | This task has a medium priority as the executive team believes this will have a large impact on the future of the publication, but since we are currently in the starting phase, other PBI's take priority | Medium-high priority | 1
| As a member of the executive team, | I want to see a 50 word blurb on the new opening of the Ottawa store including the location and a simple map of the location. | So that I can see the grand opening of the new store and assist the reader to see the expansion and the location of the new store | 15 | The newsletter shows the clearly the grand opening and the reader easly can find the location on the map | It is important to show the readers the expansion and also direct them to the location using the address and the map. | Medium-high priority | 2
| As a member of the executive team, | I want the banner to have graphics and be the width of the newsletter with the company logo (red & grey) on the left and the name of the newsletter on the right of the logo, as well as have a catchy name for the newsletter and have a graphic version of the name in the banner | So that I can input our company logo and other information to appeal to the reader | 20 | Banner must have graphics and be the same width of the newsletter. The newsletter must have a catchy name, as well as a graphic version of the name in the banner | This task has a medium-high priority due to the fact the company can still send out newsletters without having the ideal template ready. While this should be avoided, insuring that the higher priority PBI's would give us a better outcome | Medium-high priority | 2
| As a member of the executive team, | I want an editorial column that emphasizes why customized and specialized office solutions are needed, | So that I can appeal to the readers interests and promote the organization's area of specialty. | 30 | This section must be between 150-250 words discussing why specialized office solutions are needed now more than ever. | This task has a medium-high priority because it will provide significant value and interest to customers, but it is not critical to the completion of the first draft of the publication. | Medium-high priority | 2
| As a member of the executive team, | I want the newsletter to have a footer with three small pictures in a row of CustomOffice's leading products, social media buttons, contact information, and an unsubscribe link. | So that I can provide readers with information on CustomOffice's products, contact information, social media pages, and newsletter subscription options. | 35 | The footer for the newsletter should have three small pictures in a horizontal row of the leading products of CustomOffice. In addition, it should include social media buttons (Facebook and Twitter), and the contact information for the company (including an address and telephone number). The footer must also have an unsubscribe link. | This task has a medium priority because the first draft will be read by employees and stakeholders who will have access to this information. | Medium priority | 2
| As a member of the executive team, | I want the newsletter to have a signup box where subscribers can enter their email address and first and last name, | So that I can contact and share information about the newsletters and the company to interested customers. | 40 | The newsletter signup box must have a section for users to input their first and last name, and an email address. | This task has a medium-low priority, since it will not be critical to the publication of the first draft of the newsletter. However, it will be an important feature for the final draft, since it will capture a wider customer base. | Medium-low priority | 2
| As a member of the executive team, | I want the newsletter to have a feedback and commentary box with a title where readers can post questions and commentary and submit it, | So that I can gather input, questions, and concerns from customers to improve the newsletter and customer experience for future publications. | 25 | The newsletter commentary and feedback box must include a title, text area where they will type questions or comments, and a submit button. | This task has a medium-low priority because it is not critical to the publication of the first draft of the newsletter. However, it will be an important feature for the final draft, as it will allow customers to communicate to the company their experiences, concerns, and questions. | Medium-low priority | 3
| As a member of the executive team, | I want a link on the newsletter which directs to a survey, as well as a text box explaining the importance of the survey | So that I can receive feedback from the end user by method of a survey. This will help me understand what type of information our users would like to see. | 20 | Newsletter must have link to survey. Survey must have a title, as well as instructions on how to complete survey, and why they should do the survey | This task has a low priority due to the fact that the survey is a "secondary" part of the newsletter. Once we insure our publication's "template" is complete, then we will go back and edit our feature stories | Low priority | 3
| As a reader, | I want the newsletter to have a customer testimonial, | So that I can understand that CustomOffice can really provide unique solutions. | 15 | The newsletter contains a 100-250 word customer testimonial quote that emphasizes how CustomOffice can provide unique solutions. | This task has a low priority because it is not critical to the functionality and completion of the newsletter itself. It will not provide as much value to the reader or company as the other PBI items will. | Low priority | 3
| As a member of the executive team, | I want the publication to have a "Question of the Week" field | So that I can answer questions that the readers may have about our products. | 15 | The question of the week should have between 100-300 words, 1 picture, and a standout phrase: "yes, you can adjust that" | This task has a low priority because it not critical to the overall publication and provides low value compared to the other product backlog items. | Low priority | 3
| As a member of the executive team, | I want a tech tip to appear in the newsletter on how to use comments in PowerPoint | So that I can potentially assist the end user with features they may have not known of before | 15 | Must be between 75-125 words | While this is a nice feature to have for our customers, we believe that only a small portion of the customer base will be actively using it | Low priority | 3
|  |  | Sprint Backlog Total: | 375
|  |  | Sprint 1 Total: | 145
|  |  | Sprint 2 Total: | 140
|  |  | Sprint 3 Total: | 90

## DoD, Velocity, # of Sprints
Product Backlog
| Newsletter Project | Velocity Calculations
| Defintions of Done (DoD) | Reference Story = 10 points
| All coding and text complete and checked | 375 total story points for product backlog
| All links tested and insured they are working | 40% of total product backlog expected to be completed in Sprint 1
| Newsletter contains relevant graphics and articles | 375 * 0.4 = 150 points for sprint 1
All acceptance criteria is met for each task
Upload the final copy into the server under the appropriate database catalog
Calculations for the # of Sprints Required for the Product Backlog
150 points per sprint. Since we need a total of 375 points, it will take us a total of 3 sprints to complete

## Completed Product Backlog Items
Completed Product Backlog Items (completed PBI's)
| Project Name: | Newsletter Project
| User Story or Feature (Functionality) |  |  | Estimate in Points | Acceptance Criteria | Rationale for Priortization | Notes | Sprint #
| As a | I want to | So that I can